## Roadmap Delivery
Feature / Epic | Product / Area | Original Commit Date | Current Forecast Date | Actual Completion Date | Status | On Time? | Rebaselined? | Delay / Risk Reason | Dependency / Blocker (Optional) | Owner | Your Action / Intervention | Evidence Link
Epic DEMO-101: Customer Portal Accessibility Upgrade | Customer Experience | 2025-01-31 | 2025-02-14 | 2025-02-12 | Completed | No | Yes | Additional accessibility findings expanded the testing scope. | Specialist review availability | Delivery Lead | Replanned testing, secured reviewer capacity and tracked closure through weekly checkpoints. | Portfolio evidence – Demo 101
Epic DEMO-102: Self-Service Account Management | Customer Experience | 2025-03-15 | 2025-03-15 | 2025-03-14 | Completed | Yes | No |  | None | Product Owner | Maintained scope discipline and completed readiness reviews before release. | Portfolio evidence – Demo 102
Feature DEMO-103: Unified Operational Metrics | Reporting & Insights | 2025-04-30 | 2025-05-16 |  | Delayed |  | Yes | Source-data mapping required more validation than originally estimated. | Data definitions awaiting business approval | Reporting Lead | Established a decision log, named approvers and introduced twice-weekly resolution reviews. | Portfolio evidence – Demo 103
Epic DEMO-104: Partner Data Exchange | Integration Services | 2025-05-30 | 2025-05-30 |  | On Track |  | No |  | External partner certification window | Integration Lead | Confirmed certification dates and added a contingency window to the delivery plan. | Portfolio evidence – Demo 104
Feature DEMO-105: Service Health Notifications | Platform Enablement | 2025-06-20 | 2025-06-27 |  | At Risk |  | Yes | Monitoring thresholds require agreement across support and engineering teams. | Support model decision pending | Engineering Manager | Facilitated threshold workshop and documented go-live acceptance criteria. | Portfolio evidence – Demo 105
Epic DEMO-106: Knowledge Search Modernisation | Employee Experience | 2025-07-31 | 2025-07-31 |  | On Track |  | No |  | None | Product Owner | Created phased milestones and aligned content owners to weekly readiness checks. | Portfolio evidence – Demo 106
Feature DEMO-107: Automated Compliance Evidence | Governance & Risk | 2025-04-18 | 2025-04-25 | 2025-04-24 | Completed | No | Yes | A policy clarification was required before final validation. | Policy interpretation | Risk Lead | Escalated the decision early and protected the deployment window. | Portfolio evidence – Demo 107
Epic DEMO-108: API Usage Analytics | Integration Services | 2025-08-29 | 2025-09-12 |  | At Risk |  | Yes | Non-functional testing uncovered higher-than-expected data volumes. | Performance-test environment capacity | Technical Lead | Prioritised test scenarios and secured temporary capacity for validation. | Portfolio evidence – Demo 108

## Release Readiness
Release / Version | Release Date | Testing Complete? | Security Complete? | Monitoring Ready? | Alerts Ready? | Rollback Plan? | Support Ready? | Go / No-Go Approved? | Post-Release Review Done? | Incident / Defect Summary | Owner | Evidence Link
Customer Portal v2.1 | 2025-02-14 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | One minor display defect resolved during the support window. | Release Lead | Demo release record 201
Operational Metrics v1.0 | 2025-05-16 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No | Post-release review scheduled for the following week. | Reporting Lead | Demo release record 202
Partner Data Exchange v1.3 | 2025-05-30 | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | No production incidents recorded. | Integration Lead | Demo release record 203
Service Notifications v1.0 | 2025-06-27 | Yes | Yes | No | No | Yes | Yes | No | No | Alert thresholds are awaiting final operational approval. | Engineering Manager | Demo release record 204
Knowledge Search v3.0 | 2025-07-31 | Yes | Yes | Yes | Yes | Yes | No | No | No | Support training remains in progress. | Product Owner | Demo release record 205
API Analytics v1.0 | 2025-09-12 | No | Yes | Yes | Yes | Yes | Yes | No | No | Performance testing is still in progress. | Technical Lead | Demo release record 206

## RAID
ID | Type (Risk/Dependency) | Description | Date Identified | Impact | Owner | Target Resolution Date | Status | Days Open | Escalated? | Mitigation / Next Action | Resolved Date | Delivery Impact Avoided / Result
R001 | Risk | Operational monitoring thresholds may not be approved before release. | 2026-08-18 | Potential delay to production approval. | Engineering Manager | 2026-09-08 | Monitoring | 15 | Yes | Run an approval workshop and agree minimum launch thresholds.
D001 | Dependency | External partner certification is required before integration go-live. | 2026-08-12 | Release could miss the planned deployment window. | Integration Lead | 2026-09-05 | In Progress | 21 | No | Track certification evidence twice weekly and retain contingency capacity.
R002 | Risk | Specialist testing capacity is shared across two priority initiatives. | 2026-07-06 | Testing completion may move by one sprint. | Delivery Lead | 2026-07-24 | Resolved | 16 | Yes | Rebalanced the test plan and secured temporary reviewer support. | 2026-07-22 | Testing completed without moving the release date.
I001 | Issue | Business approval for reporting definitions is overdue. | 2026-08-21 | Dashboard build cannot complete final validation. | Product Owner | 2026-09-04 | Escalated | 12 | Yes | Named final approvers and scheduled a decision meeting.
A001 | Assumption | Support team training will be completed one week before launch. | 2026-08-25 | Late training could weaken initial production support. | Support Lead | 2026-09-18 | Monitoring | 8 | No | Review training completion in weekly release-readiness meetings.
Formulas:
Days Open = IF([Date Identified]="","",IF([Resolved Date]<>"",[Resolved Date]-[Date Identified],TODAY()-[Date Identified]))

## Discovery Gate
Feature / Epic | Product Brief Approved? | Approval Date | Experiment / Evidence 1 | Experiment / Evidence 2 | Success Metric Defined? | Build Start Date | Gate Passed Before Build? | Exception Approved? | Product Owner | Gap / Follow-up Action | Evidence Link
Epic DEMO-201: Intelligent Demand Forecasting POC | Yes | 2025-01-08 | Test three forecasting approaches on a balanced sample and compare accuracy. | Run the selected approach against a larger volume to assess scale, stability and cost. | Yes | 2025-01-20 | Yes | No | Product Owner | Confirm production-data retention requirements. | Demo discovery record 301
Feature DEMO-202: Customer Notification Preferences | Yes | 2025-02-03 | Interview representative users and validate the highest-value notification scenarios. | Prototype the preference journey and measure task completion. | Yes | 2025-02-17 | Yes | No | Product Manager | Validate accessibility requirements before detailed design. | Demo discovery record 302
Epic DEMO-203: Partner Onboarding Automation | No |  | Map the current onboarding journey and quantify manual hand-offs. | Pilot automated document validation with a small partner group. | No |  | No | No | Product Owner | Complete the product brief and define measurable success criteria. | Demo discovery record 303

## ADO Hygiene
Month- Year | Total Applicable Points | Fully Compliant Items | Compliance % | Missing Parent | Missing Estimate | Missing CapEx/OpEx | Missing Time Data | Other Missing Fields | Corrective Action | Evidence / Query Link
2025-01-01 | 620 | 604 | 97.42% | 6 | 3 | 5 | 2 | Four items require owner or target-date updates. | Owners contacted; corrections tracked in the weekly hygiene review. | Demo query – Jan
2025-02-01 | 645 | 635 | 98.45% | 3 | 2 | 3 | 2 | Two support items use an approved exception. | Exceptions documented and remaining gaps assigned. | Demo query – Feb
2025-03-01 | 670 | 664 | 99.1% | 2 | 1 | 2 | 1 | One new initiative is awaiting financial classification. | Product and finance owners aligned on the classification date. | Demo query – Mar
2025-04-01 | 688 | 684 | 99.42% | 1 | 1 | 1 | 1 | Four fields remain incomplete across three items. | Corrections included in the next backlog-refinement session. | Demo query – Apr